## Overview
Wave 3
Integration Name | Payroll | Planned | Executed | Passed | Failed | File Sent | Blocked | Invalid | % Passed
INT302 Internal System Test |  | 90 | 87 | 87 | 0 | 0 | 0 | 3 | 100
INT302 End to End Testing |  | 90 | 90 | 41 | 1 | 40 | 2 | 6 | 100
TOTAL |  | 180 | 177 | 128 | 1 | 40 | 2 | 9 | 200

## Master Scenarios
[7 empty] | System Integration Testing Internal |  |  |  |  | End to End Testing |  |  |  |  | Back up Data |  |  |  |  | Sage Columns
Test Case ID | Requirement ID | Business Process | Test Conditions | Expected | Tester | Pay Group / Country | Status | Test Data Used | Jira No | File Name | Comment | Status | Date Sent | File | Test Data Used | Comment | Status | Date Sent | File | Workday Link | Comment | Sage Status | Sage System Processing
TS_SSA_013 |  | File Validation | Format for the file being delivered is as per the specification | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA |  | Pass |  |  |  |  | Pass | 2019-06-05 | All | As Sage team is able to load the tests files the scenario is passed | [6 empty] | N/A
TS_SSA_005 |  | Change Personal Information | Personal Details - Change Address | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Vizeum | Pass | Bismark Odoom 63002362 Legacy 18044 - 1 Back Lane, Ghana City |  | SSA-20190530-132834-ETO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152838.htmld | Pass | 2019-06-05 | SSA-20190605-084408-ETO.csv.pgp | Tessa Smith 63002062, John Brown South Africa (Pty) Ltd, 026_001 55 Pizza Road, Cape Toen, 4567 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153207.htmld |  | Pass | Successfully processed with all fields updated as per source data
TS_SSA_007 |  | Change Personal Information | Personal Details - Change Gender | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Crimson Room Communication (Pty) Ltd | Pass | Hope Gwalo 63002072, Legacy 056 - Male |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84498.htmld | Pass | 2019-06-05 | SSA-20190605-084408-ETO.csv.pgp | Tessa Smith 63002062, John Brown South Africa (Pty) Ltd, 026_001 55 Now Male. Also added Countyr of birth and Ethnicity field |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153207.htmld |  | Pass | Successfully updated to Male Gender and Mr as Title
TS_SSA_009 |  | Change Personal Information | Personal Details - Change Legal First and Last Name | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Crimson Room Communication (Pty) Ltd | Pass | Hope Gwalo 63002072 Legacy 056, Changed Name to TestHope TestGwalo |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84498.htmld | Pass | 2019-06-05 | SSA-20190605-084408-ETO.csv.pgp | Tessa Smith 63002062, John Brown South Africa (Pty) Ltd, 026_001 55 New Name TessaTest SmithTest |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153207.htmld |  | Pass | Successfully updated to TessaTest and SmithTest
TS_SSA_015 |  | File Validation | Changes to Existing Employees - Check if the Output file appears with all the mandatory fields as per the relevent technical specification document. | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA |  | Pass |  |  |  |  | Pass | 2019-06-05 | SSA-20190605-084408-ETO.csv.pgp | Confirm if the the mandatroy files came out for test 008 - Tessa Smith | [6 empty] | Pass | Update successful with no mandatory field errors or warnings
TS_SSA_001 |  | Change Benefits | Add Dependent | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | ZA - Aegis Media Central Services (Pty) Ltd | Pass | Aashiqa Petersen (63002077) - Child - Son (Andy Petersen 01-01-2015) Saskia Daniels (63002089) - Benefit Plan - Medical Aid (ZAF) - Discovery Health Core Series - Classic Core (01-05-2019) Daughter - Sharon Daniels dob - 10-02-2010 Son - Steve Daniels dob - 03-03-2019 Amy Daniels - dob - 07072014 | 4236 4239 |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153323.htmld | File Sent | 2019-06-05 | SSA-20190605-093713-BEN.csv.pgp | Lungelo Fakude (63007941), Aegis Media Central Services (Pty) Ltd 2704, Medical Aid (ZAF) - Discovery Health Comprehensive Series - Calssic Delta Comprehensive, Life Insurance (ZAF) - Discovery Life 3x (Employee Only), Life Insurance (ZAF) - Discovery Life 3x (Employee Only), Income Disability (ZAF) - Discovery Life (Employee Only, Group Retirement Annuity (ZAF) - Allan Gray 10%. Added 2 child dependents |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153223.htmld
TS_SSA_002 |  | Change Benefits | Add New Benefit Election | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | ZA - Aegis Media Central Services (Pty) Ltd | Pass | Aashiqa Petersen (63002077) - 29/05/2019 - added Benefit Plan - Medical Aid (ZAF) - Discovery Health Comprehensive Series - Classic Comprehensive (Employee + Child), Income Disability (ZAF) - Discovery Life (Employee Only) - 75% of Salary, Life Insurance (ZAF) - Discovery Life 3x (Employee Only) - 3 X Salary, Group Retirement Annuity (ZAF) - Allan Gray 10% |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153323.htmld | File Sent | 2019-06-05 | SSA-20190605-093713-BEN.csv.pgp | Lungelo Fakude (63007941), Aegis Media Central Services (Pty) Ltd 2704, Medical Aid (ZAF) - Discovery Health Comprehensive Series - Calssic Delta Comprehensive, Life Insurance (ZAF) - Discovery Life 3x (Employee Only), Life Insurance (ZAF) - Discovery Life 3x (Employee Only), Income Disability (ZAF) - Discovery Life (Employee Only, Group Retirement Annuity (ZAF) - Allan Gray 10%. Added 2 child dependents |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153223.htmld
TS_SSA_014 |  | File Validation | New Hires - Check if the Output file appears with all the mandatory fields as per the relevent technical specification document. | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA |  | Pass |  |  |  |  | Pass | 2019-06-05 | SSA-20190605-093713-ETO.csv.pgp | Confirm with test 023 | [6 empty] | Pass | Successfully created with no mandatory field issues.
TS_SSA_023 |  | Hire - New Hire | New Hire - in Current Pay Period - Full time with All Comp grades | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - Full Circle Media (Pty) Ltd | Pass | Worker; TestBob Test 63026976, date 20052019 Perm, testbob@noemail.com, Dob 01011990, single, male, SA ID 9001015234015, Probation 20082019, Work location Johannesburg - 1st Floor, Illovo Junction, Salary 30000, Cellphone Allowacne 300, Incentive 200, medical 250, Subsistence 400, Travel 100, Bank 250655 FNB 52875484312 | 4246 | SSA-20190530-133305-ETO.csv.pgp and SSA-20190530-133305-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152886.htmld | Pass | 2019-06-05 | SSA-20190605-093713-ETO.csv.pgp, SSA-20190605-093713-PAY.csv.pgp | TestWill Test 63029237. John Brown South Africa (Pty) Ltd, hire date 03062019, probation date 03082019, permanent, work address Cape Town - Mezzanine Level, West Block, 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa, Single White Male, dob 01011990, SA ID 9001015234015, tax ref id 4566454223, Salary 40000 monthly, allownces cell 300, incentive 200, medical 300, subsistence 400, travel 500, OTP spot bonus 20000 Bank 632005 ABSA 4049232641. Home address 1Pizza Plaza, cape Town 4567, home phone 4567432, email testwill@noemail.com |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153223.htmld |  | Pass | Fields for paypoint, RSCCode and Nature of contract imported successfully. Pay file still to be confirmed
TS_SSA_006 |  | Change Personal Information | Personal Details - Change Date Of Birth | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Crimson Room Communication (Pty) Ltd | Pass | Hope Gwalo 63002072, Legacy 056 - New Dob 010190. |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84498.htmld | Pass | 2019-06-05 | SSA-20190605-094434-ETO.csv.pgp | Fidelia Igwe (63002466) Aegis Media Nigeria, 230003, New dob 01011990 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153226.htmld |  | Pass | Birth Date updated
TS_SSA_008 |  | Change Personal Information | Personal Details - Correct/Change a Govt. ID | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Crimson Room Communication (Pty) Ltd | Pass | Hope Gwalo 63002072, Legacy 056 New ID 9001015456014 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84498.htmld | Pass | 2019-06-05 | SSA-20190605-094434-ETO.csv.pgp | Fidelia Igwe (63002466) Aegis Media Nigeria, 230003, New Nat ID 34567565442 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153226.htmld |  | Pass | ID number updated correctly
TS_SSA_010 |  | Change Personal Information | Personal Details - Change Mobile Number | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Vizeum | Pass | Bismark Odoom 63002362 Legacy 18044 - New phone no. 654645644 |  | SSA-20190530-132834-ETO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152838.htmld | Pass | 2019-06-05 | SSA-20190605-094434-ETO.csv.pgp | Fidelia Igwe (63002466) Aegis Media Nigeria, 230003, New phone no. 02 345 6789 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153226.htmld |  | Pass | Number updated as per source data
TS_SSA_011 |  | Change Personal Information | Change Preferred Name | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Vizeum | Pass | Bismark Odoom 63002362 Legacy 18044 - BismarkTest OdoomTest |  | SSA-20190530-132834-ETO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152838.htmld | Pass | 2019-06-05 | SSA-20190605-094953-ETO.csv.pgp | Jonathan Teye (63002395) Ghana Carat, 18027, Preferred name - John | [6 empty] | Pass | Known as name updated in Sage
TS_SSA_025 |  | Hire - New Hire | New Hire in Previous pay period - Full Time | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Nigeria Pay Group | Pass | Testben Test 63026990, hire date 08/04, probation 08/06, single male, id 32432455445, home address 4 back lane lagos, phone 2342345453, testben@noemail.com, Lagos - 95B Oduduwa Crescent | 4226 and 4237 | SSA-20190530-134612-ETO.csv.pgp and SSA-20190530-134612-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153387.htmld | Pass | 2019-06-05 | SSA-20190605-102030-ETO.csv.pgp and SSA-20190605-102030-PAY.csv.pgp | TestJulie Test 63029239, Aegis Media Nigeria Hire date 06052019, Probation 06052019. Work Location 95B Oduduwa Crescent, Ikeja GRA&#xa;Lagos 100271&#xa;Lagos&#xa;Nigeria, Lagos - 95B Oduduwa Crescent, Married female, dob 01011990, Nat ID 34223432543, Salary 74239.80 Annual, CTC Allownace 13th Month, Clothing, Employee Benefit, Housing, Leave, Meal, Medical, Pension, Telephone, Transport, Utility. Home Address, 3Pasta Place, Lagos, Phone 345354, email testjulie@noemail.com |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153235.htmld |  | Pass | New employee created in the current pay period with previous period engagement date
TS_SSA_026 |  | Hire - New Hire | New Hire Part Time | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Carat | Pass | testjose test, 63026978, mamager andrew ackah, hire date 20052019, pt perm, 20 hour week, Accra - 33 Justice DF Annan Street, testjose@noemail.com, dob 01011990, single male, SSIN 1234567890123, Salary 16215, clothing allowance 30 night duty 50, phone 70, regular 90, Bank 030100, Barclays, 0003245156074 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84645.htmld | Pass | 2019-06-05 | SSA-20190605-102030-ETO.csv.pgp and SSA-20190605-102030-PAY.csv.pgp | Testjuan Test 63029240, Ghana Carat, Hire date 03062019, probabtion end date 22072019, work address 33 Justice DF Annan Street, Tesano Village, Accra&#xa;Accra&#xa;Ghana, Single Male, dob 01011990, Social Sec 1234567891234, Salary 10000, Clothing 300, Night 400, phone 250, regular 100, OTP Referral 2000, Bank 130100, 2526491204829, Home address 2 Sandwich Street, acrra, phone 3453435 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153235.htmld |  | Pass | New hire created successfully
TS_SSA_033 |  | Job Change | Change Job - Change Hours - full time to part time | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | Nadia Jackson 63002249 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153219.htmld | Pass | 2019-06-05 | SSA-20190605-102640-ETO.csv.pgp | Alecia Erasmus (63002094) John Brown South Africa (Pty) Ltd 119_001, changed to pt. New Salary 16979.35 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153238.htmld |  | Pass | Updated and Period Salary field in Sage matches (Note that the Sage Employee Code for this person is 119_001)
TS_SSA_034 |  | Job Change | Change Job - Change Hours - part time to full time | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass |  |  |  |  | Pass | 2019-06-05 | SSA-20190605-102640-ETO.csv.pgp | Anna Van Wyk (63002178), MEC Carat (Pty) Ltd 2382, changed to ft - new salary 48684.87 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153238.htmld |  | Pass | Period Salary value updated
TS_SSA_038 |  | Job Change | Change Job - Edit Position - Job Title change - No other changes | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | Nadia Jackson 63002249 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153219.htmld | Pass | 2019-06-05 | SSA-20190605-102640-ETO.csv.pgp | Ernest Arinmah (63002463) Aegis Media Nigeria 230096, New Title - Manager - no output expected |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153238.htmld |  | Pass | No record processed to Sage
TS_SSA_040 |  | Job Change | Change Job - Transfer - Change Location - no other changes | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | 63002250 2498 |  |  |  | Pass | 2019-06-05 | SSA-20190605-102640-ETO.csv.pgp | Clare Trafankowska (63002313), MEC Carat (Pty) Ltd, 2671, New address Cape Town - Mezzanine Level, West Block |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153238.htmld |  | Pass | Record came through and paypoint was updated in Sage with the new location
TS_SSA_057 |  | Maintain Payment Elections | Change Bank Details - Payroll | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - John Brown South Africa (Pty) Ltd | Pass | Ricardo Bobbert 63002052, Account no. 1212121212 Univeral 045003. Savings Account |  | SSA-20190530-133911-ETO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152924.htmld | Pass | 2019-06-05 | SSA-20190605-103446-ETO.csv.pgp | Reza Allie (63002115) John Brown South Africa (Pty) Ltd, 051001 STDBANK 51326361 Savings |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153241.htmld |  | Pass | A new record with the banking details was created. Note that for auditing purposes Sage will always create a new bank detail record even for changes
TS_SSA_064 |  | Probation Period | Extend/Change Probation period/ Pérode essai | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - Full Circle Media (Pty) Ltd | Pass | TestBob Test 6302976 - Changed Probation end date from 20/05/19 to 01/09/19 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152936.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Tornye Avortri (63022098), Ghana Carat, Probation end date 30/08/2019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Date changed as per the source file
TS_SSA_068 |  | Request Compensation Change | Comp Change - Change Pay - no other changes in current pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - Aegis Media Central Services (Pty) Ltd | Pass | Bongiwe Sithole 012, New Salaey 12112. (also input racialgroup field W3_ZAF_African_Black) |  | SSA-20190530-131820-ETO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152950.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Sikota Bones (63006951), Dentsu Aegis Network Zambia, 240003,, New Salary 1000000, |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Salary value changed successfully
TS_SSA_069 |  | Request Compensation Change | Comp Change - Change Pay - no other changes in previous pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | KE - Dentsu Aegis Network Kenya | Pass | Bongiwe Sithole 012, New Salaey 12112. (also input racialgroup field W3_ZAF_African_Black) |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152956.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Monica, Marcjanek (63002071), Crimson Room Communication (Pty) Ltd, 054_C15, Salary 35000 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Salary change made, however this is only effective from the active period. Previous backpay would need to be loaded manually
TS_SSA_072 |  | Request Compensation Change | Negative Comp Change in current pay period - Change Pay - no other changes | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - Aegis Media Central Services (Pty) Ltd | Pass | Lana Marais 63002174 - changed comp to 60000 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152995.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Estelle Dietrich (63002059) John Brown South Africa (Pty) Ltd, 021_001. Salary 20000 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Salary value overridden with the latest value
TS_SSA_078 |  | Termination | Termination - End Contract for Fixed Term Employee | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | Tanzania Pay Group | Pass | Abisay Allen 63002355 (Fixed term contract) - termination date - 23/05/2019 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152883.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Sajidu Kiobya (63007738) Aegis Media Tanzania, 16023, Resigned 03062019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Termination Date updated correctely and reason also updated
TS_SSA_080 |  | Termination | Termination - Permanent Employee - Involuntary in previous pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | KE - Isobar Kenya/Kenya | Pass | Joy Maina 63007917/termination date - 29/04/2019 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84565.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Mogamat Daniels (63002171) Aegis Media Central Services (Pty) Ltd, 2305, Dismissed 06052019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Termination Date updated correctely and reason also updated
TS_SSA_081 |  | Termination | Termination - Permanent Employee - Voluntary in current pay period and OTP | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | GH - Ghana Vizeum | Pass | Donna Agbo - 63002368 otp/500 GHS - Termination date - 28/05/2019 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153013.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Alex Muiruri (63024792) Posterscope Kenya OTP , Resigned |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Termination Date updated correctely and reason also updated
TS_SSA_082 |  | Termination | Termination - Permanent Employee - Voluntary in future pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | Nigeria Pay Group | Pass | Adaora Aninye 63002436 / termination date - 01/06/2019 |  |  |  | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Noimot Junaid (63002493), Nigeria Pay Group 230111, 01082019 Resigned - no output expected |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | No employee record received
TS_SSA_083 |  | Termination | Termination - Permanent Employee - Voluntary in previous pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | Nigeria Pay Group | Pass | Taiwo Mogaji (63002513)/termination date - 10/04/2019 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153079.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp | Chris Addo (63022106) Ghana Vizeum, Reigned 01052019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass | Record successfully terminated with previous resignation value
TS_SSA_079 |  | Termination | Termination - Permanent Employee - Involuntary in current pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | ZA - Aegis Media Central Services (Pty) Ltd/South Africa | Pass | Lynne Lawrence 63002173/termination date - 22/05/2019 |  | SSA-20190522-145021-ETO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84553.htmld | Pass | 2019-06-05 | SSA-20190605-104230-ETO.csv.pgp; SSA-20190605-104230-PAY.csv.pgp | Angela Childs (63002118) John Brown South Africa (Pty) Ltd, 163, Constructive Dismissal, 03062019, OTP Termination Pay 10000 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Pass/PAY still to be confirmed | Termination successfully processed and reason data matches
TS_SSA_018 |  | File Validation | Verify Behaviour when No Employee is output. | A blank file should/Shouldn't be generated as per the relevent Tech Specification | JA |  | Pass | No output for future pay period comp changes |  |  |  | File Sent | 2019-06-05 | SSA-20190605-104230-PAY.csv.pgp | Samantha Kipury (63002423), Dentsu Aegis Network Kenya, 5005, New Salary 1000000, Cell allowance 1000, date 05082019 - future dated - no output expected | [6 empty] | Still to be processed after ETO testing is up to date
TS_SSA_065 |  | Request Compensation Change | Comp Change - Add Recurring Allowance - All Eligible Allowances for the Country | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA |  | Pass | Same Data as test 23 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152886.htmld | File Sent | 2019-06-05 | SSA-20190605-104230-PAY.csv.pgp | Kofi Owusu (63002399), Ghana Vizeum 18035, Clothing 200, Night 100, Phone 400, Regular 150 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Still to be processed after ETO testing is up to date
TS_SSA_066 |  | Request Compensation Change | Comp Change - Add Recurring Allowance to Employee in previous pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Vizeum | Pass | Fuseini Seidu Sahanoon 18038 effective date 080419. Clothing 1000, night 200, phone 300, regular 100 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152942.htmld | File Sent | 2019-06-05 | SSA-20190605-104230-PAY.csv.pgp | Eunice Lyimo (63007739) Aegis Media Tanzania, 16022, Acting 300000, Housing 200000, Leave 50000, Travel 40000 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Still to be processed after ETO testing is up to date
TS_SSA_067 |  | Request Compensation Change | Comp Change - Change Pay, Allowance, Period Salary in future pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Aegis Media Tanzania | Pass | Abdul Skyes 16008 - Effective Date for changes 01072019 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152948.htmld no output as future dated | File Sent | 2019-06-05 | SSA-20190605-104230-PAY.csv.pgp | Samantha Kipury (63002423), Dentsu Aegis Network Kenya, 5005, New Salary 1000000, Cell allowance 1000, date 05082019 - future dated - no output expected |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153244.htmld |  | Still to be processed after ETO testing is up to date
TS_SSA_003 |  | Change Benefits | Change Benefit Election | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF |  | Pass | Lillian Monageng (63002345) - 01/05/2019 - added Benefits Medical Aid (ZAF) - Discovery Health Comprehensive Series - Calssic Delta Comprehensive - (Employee Only) Income Disability (ZAF) - Discovery Life (Employee Only) - 75% of Salary, Life Insurance (ZAF) - Discovery Life 3x (Employee Only) - 3 X Salary, Group Retirement Annuity (ZAF) - Allan Gray 10% |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153326.htmld | File Sent | 2019-06-06 | SSA-20190606-124345-BEN.csv.pgp | Lynne Lawrence (63002173) Aegis Media Central Services (Pty) Ltd 2320 - changed to married. Added husband - given Medical Aid (ZAF) - Discovery Health Comprehensive Series - Calssic Delta Comprehensive and Life Insurance (ZAF) - Discovery Life 5x (Employee Only) |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153252.htmld |  | Still to be processed after ETO testing is up to date
TS_SSA_004 |  | Change Benefits | Change in Maritial status and Add / Remove dependent | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF |  | Pass | Lillian Monageng (63002345) - 01/05/2019 - added Benefits Medical Aid (ZAF) - Discovery Health Comprehensive Series - Calssic Delta Comprehensive - (Employee Only) Income Disability (ZAF) - Discovery Life (Employee Only) - 75% of Salary, Life Insurance (ZAF) - Discovery Life 3x (Employee Only) - 3 X Salary, Group Retirement Annuity (ZAF) - Allan Gray 10% |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153326.htmld | File Sent | 2019-06-06 | SSA-20190606-124345-BEN.csv.pgp | Lynne Lawrence (63002173) Aegis Media Central Services (Pty) Ltd 2320 - changed to married. Added husband - given Medical Aid (ZAF) - Discovery Health Comprehensive Series - Calssic Delta Comprehensive and Life Insurance (ZAF) - Discovery Life 5x (Employee Only) |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153252.htmld |  | Still to be processed after ETO testing is up to date
TS_SSA_017 |  | File Validation | Insert Separators used in the integrations & Special Characters on free text fields like Job Title, Description. | This should not break the integration output file. | JA | KE - Isobar Kenya | Pass | 63007882 Legacy Changed first name to B"eve"rly,,,!!!", and address line 1 to "1lane",road¦¦ |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153121.htmld | File Sent | 2019-06-06 | SSA-20190606-124813-ETO.csv.pgp | Santi Van Zyl (63002322) Trigger Communication Consulting (Pty) ltd 457 - changed name to ¦¦;"Santi", "Van Zyl",-./" |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153255.htmld |  | Failed to load file due to special characters | Check regarding Country Code Field Names Andy to Raise CR after Sage Team's requirement email
TS_SSA_035 |  | Job Change | Change Job - Change Job Profile and Grade change in current pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | 63002208 Grade U to Grade B |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153308.htmld | Pass | 2019-06-06 | SSA-20190606-125247-ETO.csv.pgp and SSA-20190606-125247-PAY.csv.pgp | Luchritia Vuba (63002058) John Brown South Africa (Pty) Ltd 018_001. Promoted to Designer on 03062019, Salary 40000, Allowances Cell 300, Incentive 200, Medical 300, Subsistence 400, Travel 500. New address 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa. New Profile and Comp Grade wont have an output. |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153258.htmld |  | Pass | Record updated with latest salary, however no job details are interfaced for update
TS_SSA_037 |  | Job Change | Change Job - Change Position - Promotion with Comp Changes | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | 63002250, 2589 |  | SSA-20190529-141804-ETO.csv.pgp, SSA-20190529-141804-PAY.csv.pgp, SSA-20190529-141804-BEN.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153307.htmld | Pass | 2019-06-06 | SSA-20190606-125247-ETO.csv.pgp and SSA-20190606-125247-PAY.csv.pgp | Luchritia Vuba (63002058) John Brown South Africa (Pty) Ltd 018_001. Promoted to Designer on 03062019, Salary 40000, Allowances Cell 300, Incentive 200, Medical 300, Subsistence 400, Travel 500. New address 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153258.htmld |  | Pass | Record updated with salary values. No grade or title details interfaced to be updated
TS_SSA_041 |  | Job Change | Change Job - Lateral Transfer - Change Manager - in current pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification |  |  | N/A | 63002250 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153307.htmld | Pass | 2019-06-06 | SSA-20190606-125247-ETO.csv.pgp and SSA-20190606-125247-PAY.csv.pgp | Luchritia Vuba (63002058) John Brown South Africa (Pty) Ltd 018_001. Promoted to Designer on 03062019, Salary 40000, Allowances Cell 300, Incentive 200, Medical 300, Subsistence 400, Travel 500. New address 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153258.htmld |  | Pass | Record updated with salary values. No grade or title details interfaced to be updated
TS_SSA_036 |  | Job Change | Change Position - Demotion with Comp Changes | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | Nadia Jackson 63002249 |  | SSA-20190528-095545-ETO.csv.pgp SSA-20190528-095545-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153219.htmld | File Sent | 2019-06-06 | SSA-20190606-130106-ETO.csv.pgp and SSA-20190606-130106-PAY.csv.pgp | Demotion: Richard Lewis (63002064) John Brown South Africa (Pty) Ltd 033_C15, Now is a designer. Salary 40000, Allowances Cell 300, Incentive 200, Medical 300, Subsistence 400, Travel 500. New address 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153271.htmld |  | Failed | Record is seen to exist through process and causes update event. However system core process errors saying that the employee does not exist. Sage to investigate further
TS_SSA_046 |  | Job Change | Change Job in current pay period - Change Employee from Regular to Contigent worker | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | ZA - MEC Carat (Pty) Ltd | Pass | 63002305 Elizabeth Pillay terminated 14/05/19 and contracted as contingent worker to P630029169 (C02613) @ 15/05/19 |  |  | Only able to show termination as no CW output https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153334.htmld | Pass | 2019-06-06 | SSA-20190606-130657-ETO.csv.pgp and SSA-20190606-130657-PAY.csv.pgp | Temitope Johnson (Terminated) (63002425) - Ghana Carat - 18031 -terminated 050619. Started as CW on 060619 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153274.htmld |  | Pass | Record first had to be transferred in Sage. And thereafter changes processed and updated successfully
TS_SSA_039 |  | Job Change | Change Job - Promotion in previous pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | 63002208, 2498 Date:01/04/2019 |  | SSA-20190529-141930-ETO.csv.pgp, SSA-20190529-141930-PAY.csv.pgp, SSA-20190529-141930-BEN.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153308.htmld | Pass | 2019-06-06 | SSA-20190606-130657-ETO.csv.pgp and SSA-20190606-130657-PAY.csv.pgp and SSA-20190606-130657-BEN.csv.pgp | Hope Gwalo (63002072) Crimson Room Communication (Pty) Ltd 056. Date 01052019. New Address 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa. New Company John Brown South Africa (Pty) Ltd. New Salary 50000, Cell 200 Travel 500. Benefit added Group Retirement Annuity (ZAF) - Allan Gray 12.5 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153274.htmld |  | Pass | Record details updated with latest data matching
TS_SSA_042 |  | Job Change | Change Job - Transfer - Same Country different Paygroup/Company | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass | Nadia Jackson 63002249 |  |  |  | Pass | 2019-06-06 | SSA-20190606-130657-ETO.csv.pgp and SSA-20190606-130657-PAY.csv.pgp and SSA-20190606-130657-BEN.csv.pgp | Hope Gwalo (63002072) Crimson Room Communication (Pty) Ltd 056. Date 01052019. New Address 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa. New Company John Brown South Africa (Pty) Ltd. New Salary 50000, Cell 200 Travel 500. Benefit added Group Retirement Annuity (ZAF) - Allan Gray 12.5 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153274.htmld |  | Pass | Record details updated with latest data matching
TS_SSA_045 |  | Job Change | Change Job in current pay period - Convert Employee from Contigent worker to Regular | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | ZA - MEC Carat (Pty) Ltd | Pass | C01877 Wicus Swanepoel converted to employee perm position P63029168 @ 29/052019 |  | SSA-20190530-082206-ETO.csv.pgp | Only able to show hire part of process as CW has no output. Warnings were produced because of lack of mandatory fields https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84817.htmld | File Sent | 2019-06-13 | SSA-20190613-124455-ETO.csv.pgp SSA-20190613-124455-PAY.csv.pgp SSA-20190613-124455-BEN.csv.pgp | Wicus Swanepoel (63029250) John Brown South Africa (Pty) Ltd. Conversion date 06/06/19, probation 31/08/19. email Wicus.Swanepoel@caratpossibilities.com. Work 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa. White single male 010190, tax 4536356454, ID 9001015231015, Salary 40000, cell 300, incentive 200, medical 300, subsistence 400, travel 500. Benefit Group Retirement Annuity (ZAF) - Allan Gray 10% |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153386.htmld |  | Ready for Retest
TS_SSA_048 |  | Job Change | Temp to Perm in current pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | ZA - Aegis Media Central Services (Pty) Ltd | Pass | Marinda Van Rooy (c01886) CONVERTED TO Perm (63026989) 29/05/19 |  | SSA-20190530-082206-ETO.csv.pgp | Only able to show hire part of process as CW has no output. Warnings were produced because of lack of mandatory fields https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84817.htmld | File Sent | 2019-06-13 | SSA-20190613-124455-ETO.csv.pgp SSA-20190613-124455-PAY.csv.pgp SSA-20190613-124455-BEN.csv.pgp | Wicus Swanepoel (63029250) John Brown South Africa (Pty) Ltd. Conversion date 06/06/19, probation 31/08/19. email Wicus.Swanepoel@caratpossibilities.com. Work 31 Brickfield Road&#xa;Cape Town&#xa;Salt River&#xa;7925&#xa;South Africa. White single male 010190, tax 4536356454, ID 9001015231015, Salary 40000, cell 300, incentive 200, medical 300, subsistence 400, travel 500. Benefit Group Retirement Annuity (ZAF) - Allan Gray 10% |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153386.htmld |  | Ready for Retest
TS_SSA_028 |  | Hire - New Hire | New Hire Fixed Term Contract | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | KE - Dentsu Aegis Network Kenya | Pass | TestAlex Test, 63026979, manager Chris Madison,, hire date 20052019, end date 31082019, testalex@noemail.com, dob 010190, male, divorced, SSIN 34325435, NSSF 34534354353, Nairobi - Office 2, 5th floor, Salary 100000, Cellphone 1000, Parking 10000, Travel 10000 | 4234 |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84648.htmld | Pass | 2019-06-06 | SSA-20190606-135013-ETO.csv.pgp and SSA-20190606-135013-PAY.csv.pgp | Donald Trump (63029241) - Kenya Isobar Kenya hire date 04/06/19, married male, dtrump@enoemail Nat ID 35435435 NSSF 32432535. Address Office 2, 5th floor, Jadala Place&#xa;Ngong Lane off Ngong Road&#xa;Nairobi&#xa;Kenya Salary - 100,000 Travel - 30,000 Cellphone - 24,000 Parking - 60,000 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153277.htmld |  | Pass | New hired successfully processed and data matches to source
TS_SSA_029 |  | Hire - New Hire | New Hire Casual Worker | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Aegis Media Tanzania | Pass | TestAna Test 63026981, mananger Loreen Hunter, hire date 21052019, 15 hour week, single female, dob 010190, testana@noemail.com, PPF 324324243, NSSF 34232423, Comp 10000 hourly, Acting allowance 2000, Housing 1000, Leave 1000, Travel 1000 Dar Es Salaam - 1826 Chole Road, Masaki | 4235 | SSA-20190530-135507-ETO.csv.pgp and SSA-20190530-135507-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153390.htmld | File Sent | 2019-06-13 | SSA-20190613-160022-ETO.csv.pgp | Joseph Biden (63029245) - Zambia Male DIvorced SS no. 234234323. Unit C2, Garden City Mall&#xa;Great East Road&#xa;00000 Lusaka&#xa;Zambia. jbiden@email.com Bank 0034547608249294 130100 Salary - 150,000 annual Education - 5500 monthly Settling - 5000 monthly General - 10000 montly |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153277.htmld https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153389.htmld |  | Partial Pass | Record did not have Title Type, and this is a mandatory field.. Load in middle due to mandatory data missing. SSA-20190606-135013-ETO.csv.pgp and SSA-20190606-135013-PAY.csv.pgp
TS_SSA_030 |  | Hire - New Hire | New Hire Student/Intern | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Dentsu Aegis Network Zambia | Pass | TestVictor Test 63026982 manager Sikota Bones, hire date 210519, testvictor@noemail.com, single male do 01012000, end date 31072019, Comp Salary 1000 Monthly, Lusaka - Unit C2, Garden City Mall Great East Road Lusaka Zambia |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153115.htmld | Pass | 2019-06-06 | SSA-20190606-135013-ETO.csv.pgp and SSA-20190606-135013-PAY.csv.pgp | Gordon Bennett Isobar Kenya (63029247) - Kenya Male married Nat ID 2, 34554354, PIN A123456789D, NSSF 87856756654. Office 2, 5th floor, Jadala Place&#xa;Ngong Lane off Ngong Road&#xa;Nairobi&#xa;Kenya gbennett@email.com Salary - 75,000 Annual Travel - 5000 Monthly Cellphone - 1000 Monthly Parking - 10000 Monthly |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153277.htmld |  | Pass | New hired successfully processed and data matches to source
TS_SSA_060 |  | OTP | OTP - Request One Time Payment for employee (NOTE: Request ALL OTPs for Country) | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - Dentsu Aegis Amnet SSA (Pty) Ltd | Pass | Siyanda Msongelwa 63023496, Back Pay 1000, Leave Pay 1001, Overtime 2 1002, Referrral 5000, Spot 103, Termination 1000, Commission 1000, Overtime 1.5 1234, Notice 2348, Severance 5679 and 2539 Rebecca Lethoko bonus | 4240 | SSA-20190529-113543-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153287.htmld and https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153419.htmld | File Sent | 2019-06-06 | SSA-20190606-141623-PAY.csv.pgp | All entered as at 04/06/2019 Ato Abassah (63022109) - Ghana Carat Ghana - Spot Bonus 15,000.00 Ghana - Referral Payment 100.00 Ghana - Severance 250.00 Ghana - Notice pay 10,000.00 Ghana - Overtime payment 1,000.00 Global - Commission 1,200.00 Eric Mwaniki (63002377) - Kenya Isobar Kenya ISO006 Kenya - Spot Bonus 50,000.00 Kenya - Referral Payment 50,000.00 Kenya - Notice pay 10,000.00 Kenya - Overtime payment 20,000.00 Global - Commission 5,000.00 Loreen Hunter (63002401) 16018 - Tanzania Tanzania - Spot Bonus 10,000,000.00 Tanzania - Referral Payment 100,000.00 Tanzania - Notice pay 500,000.00 Global - Commission 1,000,000.00 Andrew Kakoma (63006949) 240001- Zambia Zambia - Spot Bonus 100,000.00 Zambia - Severance 25,000.00 Zambia - Service bonus 50,000.00 Zambia - Repatriation 15,000.00 Zambia - Referral Payment 1,000.00 Zambia - Overtime payment 25,000.00 Zambia - Notice Pay 50,000.00 Zambia - Leave in Lieu 40,000.00 Global - Commission 50,000.00 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153283.htmld
TS_SSA_061 |  | OTP | OTP - Request One Time Payment for employee for future pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - Vizeum Media South Africa (Pty) Ltd | Pass | Robert Stanbridge 63002054, Back Pay 010719 10000ZAR |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152927.htmld - No output as future pay period | File Sent | 2019-06-06 | SSA-20190606-141623-PAY.csv.pgp | Emelia Agyapong (63022107) - Ghana Ghana Carat - 10/07/19 (no output expected) Global - Commission 8,000.00 Ghana - Spot Bonus 5,000.00 Ghana - Severance 2,000.00 Ghana - Referral Payment 1,000.00 Ghana - Overtime payment 2,000.00 Ghana - Notice pay 1,000.00 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153283.htmld
TS_SSA_086 |  | Time Off | Time Off - All Time Off Plans for the Country | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Aegis Media Nigeria, John Brown South Africa (Pty) Ltd, GH - Ghana Carat, KE - Dentsu Aegis Network Kenya, Aegis Media Tanzania, Dentsu Aegis Network Zambia | Pass | 1. Nigeria: Chike Oputa 230112 - Annual 06/05 - 10/05, Unpaid 13/05 - 15/05, Study 1605, Sick 23/05. 2. South Africa Tessa Smith 026_001, Family Resp 21/05, Annual 13/05 - 17/05, Study 07/05, Sick 0.5 days 06/05,3. Ghana Francis Sampson 18028, Sick 2705 - 28/05, Exam 0.5 days 20/05, Sick, 13/05 - 14/05, Annual 06/06 - 08/05, 4. Kenya Joyce Swedi 5007, Annual 13/05 - 14/05, Unpaid 16/05 - 17/05, Sick 20/05 - 22/05. Exam 24/05. 5 Tanzania Henry Mbwille 16010 Annual 06/05 - 10/05, Uunpaid 14/05 - 15/05, Exam 16/05, Sick 20/05, Family 22/05, Zambia Jessica Kanyuka 240002, Annual 20/05, Unpaid 22/05 - 23/05, Exam 27/05, Family 28/05 | 4232 | SSA-20190524-091509-ATO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153247.htmld | File Sent | 2019-06-07 | SSA-20190607-124415-ATO.csv.pgp | 1. South Africa Rejoice Zharare (63002232) 2553 MEC Carat (Pty) Ltd, Sick leave 1 day 0306, Exam Leave .5 days 0406, family responsibility 1 day 0506, annual leave 7 days 0606 - 14/06 2. Ghana Mawuli De-Lima (63002404) Ghana Vizeum 18016, Unpaid leave 1 day 0306, Sick 1 day 0406, exam 1 day 0506, Annual 11 days 0606 - 2006. 3. Nigeria Abena Annan (63002434) 230009, Annual 10 days 1706 - 2806, Exam 1 day 1106, Sick 1 day 0506, Unpaid 1 day 0306. 4 Kenya, Joel Rao (63002393),Dentsu Aegis Network Kenya, Annual Leave 5 days 0306 - 0706, Unpaind 1 day 1006, Study 1 day 1106, Sick 1 day 1206. Tanzania. Dorothy Malisa (63002370),16007 Sick 0.5 days 1206 Annual 5 days 0306 - 0706, Unpaid 1 day 1006, Study 1 day 1106. 6 Zambia Sikota Bones (63006951) 240003 Annual Leave 3 days 0306 - 0506, Family 1 day 0606, sick 1 day 0706, unpaid 1 day 1006, exam 1 day 1106. |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153287.htmld
TS_SSA_020 |  | File Validation | employees without title do appear on the deliverable file | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA |  | Pass | Warnings correctly gnerated and do appear |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84776.htmld | File Sent | 2019-06-07 | SSA-20190607-130146-ETO.csv.pgp | Loreen Hunter (63002401) Aegis Media Tanzania 16018, Took off name title, also changed dob to 010190 and citizenship |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153290.htmld
TS_SSA_012 |  | Change Personal Information | Personal Details - Change Gender - Employee with Gender as Not Declared | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification |  |  | N/A | System does not allow non declarerd gender |  |  |  | N/A | [9 empty] | N/A
TS_SSA_016 |  | File Validation | Separators used on the deliverable file is as per the specification | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA |  | Pass |  |  |  |  | File Sent | 2019-06-05 |  | If data is input correctly into SAGE
TS_SSA_019 |  | File Validation | Towards the End of the test cycle, perform a Integration run for the whole pay group. | All the data is output as expected. | DP |  | Pass |  | 4241 |  | Extra line produced in all output files. https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153412.htmld | N/A
TS_SSA_021 |  | File Validation | Existing employee Type of contract change correctly shown in the file | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA |  | Pass | New Hires |  |  |  | N/A
TS_SSA_022 |  | Hire - Correction | Update Original hire date in the same pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Vizeum Media South Africa (Pty) Ltd | Pass | TestDom Test 63026984 manager Anne Rensburg, Start Date changed from 210519 to 230519 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153118.htmld | Pass | 12th June 2019 | No Files generated | 63029238, hire date changed from 5th June to 12th June 2019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153347.htmld | Jira 4247 is raised The integration is designed not to send correction or Rescind as discussed prior. The rescind on hire or a non starter needs to be handled manually
TS_SSA_024 |  | Hire - New Hire | New Hire - in Future Pay Period - Full Time | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Dentsu Aegis Network Kenya | Pass | TestWill Test 63026983 Manager Joeal Rao, Hire date 010719 |  |  | No output as future hire. https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152909.htmld | File Sent | 2019-06-05 |  | TestDom 63029238- John Brown South Africa (Pty) Ltd - future hire date 03082019, no output expected
TS_SSA_027 |  | Hire - New Hire | New Hire Contingent Worker | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | John Brown South Africa (Pty) Ltd | Pass | TestChris Test C02612, manager Meagan Kuhn, hire date 210519, end date 311219, Single Male, Dob 02011990, ID 9001025234013, Cape Town - 2nd Floor, Block A, Black River Park North |  |  | No output as CW | N/A |  |  | CW - not in integration | [6 empty] | N/A
TS_SSA_031 |  | Hire - Re-Hire | Re-Hire of an employee within a different company | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification also check Rehire of ex-employee to verify no termination date but all the other dates appear | JA | MEC Carat (Pty) Ltd and Aegis Media Central Services (Pty) Ltd | Pass | Nuraan Scott 2596 - Resigned and rehired 23/05/19 - salary 50000 | 4227 |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153055.htmld | File Sent | 2019-06-19 | SSA-20190619-145948-ETO.csv.pgp | Steve Downey terminated back in feb 2019. Now have been hired from 10/ 06/2019. |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/3$6140/2085$153447.htmld
TS_SSA_032 |  | Hire - Re-Hire | Re-Hire of an employee within a same company | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification also check Rehire of ex-employee to verify no termination date but all the other dates appear | JA | ZA - Trigger Communication Consulting (Pty) ltd | Pass | Santi Van Zyl - Legacy 457. |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153073.htmld | File Sent | 2019-06-19 | SSA-20190619-163230-ETO.csv.pgp | Cuan Bergman terminated on 31/01/2019 rehired in same company and costcenter for 19/06/2019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153469.htmld
TS_SSA_043 |  | Job Change | Change Job - Transfer Out to a Different Country | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass |  | 4242 |  | - should hire or termination come out first | Blocked
TS_SSA_044 |  | Job Change | Change Job - Transfer In from a Different Country | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | DP |  | Pass |  |  |  |  | Blocked
TS_SSA_047 |  | Job Change | Change Org Assignment - Change Cost Centre - no other changes in current pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification |  |  | N/A | No cost center output in file |  |  |  | N/A |  |  | No output in integration | [6 empty] | N/A
TS_SSA_049 |  | LOA | Leave of Absence for future pay period - ALL Payroll Impacting Leaves | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | ZA - Posterscope (Pty) | Pass | South Africa Donald Mokgale (63002343) 01/06/19 - 30/06/19 Sabbatical Donald Mokgale (63002343) 01/08/19 - 31/08/19 Unpaid Leave |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84729.htmld | File Sent | 2019-06-13 | SSA-20190613-160022-ATO.csv.pgp
TS_SSA_050 |  | LOA | Leave of Absence for previous pay period - ALL Payroll Impacting Leaves | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | ZA - Posterscope (Pty) Ltd and | Pass | South Africa Donald Mokgale (63002343) 01/04/19 - 30/04/19 Unpaid Leave |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84729.htmld | File Sent | 2019-06-13 | SSA-20190613-160022-ATO.csv.pgp
TS_SSA_051 |  | LOA | Leave of Absence in current pay period - ALL Leave Types | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | GH - Ghana Carat KE - Posterscope Kenya | Pass | Ghana - Adjoa Intsiful (63002356) - 24/05/19 - Leave of Absence (Paid) Ghana - Adjoa Intsiful (63002356) - 27/05/19 - Leave of Absence (UnPaid) Ghana - Adjoa Intsiful (63002356) - 28/05/19 - Long term sick Ghana - Adjoa Intsiful (63002356) - 29/05/19 - Maternity Ghana - Adjoa Intsiful (63002356) - 30/05/19 - Paternity Kenya - Alex Muiruri (63024792) - 02/05/19 - Leave of Absence (Paid) Kenya - Alex Muiruri (63024792) - 03/05/19 - Leave of Absence (UnPaid) Kenya - Alex Muiruri (63024792) - 06/05/19 - Long term sick Kenya - Alex Muiruri (63024792) - 07/05/19 - Maternity Kenya - Alex Muiruri (63024792) - 08/05/19 - Paternity |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84729.htmld | File Sent | 2019-06-13 | SSA-20190613-160022-ATO.csv.pgp
TS_SSA_052 |  | LOA | Leave of Absence which does not impact Payroll | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | Zambia Pay Group Tanzania Pay Group | Pass | Zambia Andrew Kakoma (63006949) - - 02/05/19 - Leave of Absence (Paid) Tanzania Loreen Hunter (63002401) - 02/05/19 - Leave of Absence (Paid) |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84729.htmld | File Sent | 2019-06-13 | SSA-20190613-160022-ATO.csv.pgp
TS_SSA_053 |  | LOA - Correction | Leave of Absence correction | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Carat | Pass | Bithia Awuku-Asante (63002363) - 06/05/2019 - 31/05/19 - corrected to end date 27/05/19 Leave of Absence Paid |  | SSA-20190528-084421-ATO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153213.htmld | File Sent | 2019-06-19 | SSA-20190619-150502-ATO.csv.pgp | Fiona November (63025485) Changed the First day of absence to 01/05/2019 to 31/12/2019 from 06/05/2019 to 31/12/2019
TS_SSA_054 |  | LOA - Correction | Correct Leave of Absence for previous pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Carat | Pass | Bithia Awuku-Asante (63002363) - Leave of Absence Unpaid - New dates 08/04/19 22/04/19 |  | SSA-20190528-084421-ATO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153213.htmld | File Sent | 2019-06-19 | SSA-20190619-150502-ATO.csv.pgp | Fiona November (63025485) Changed the First day of absence to 01/05/2019 to 31/12/2019 from 06/05/2019 to 31/12/2019
TS_SSA_055 |  | LOA - Rescind | Rescind LOA | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | GH - Ghana Carat | Pass | Reginald Kumtsiah-Turkson - (63022096) 01/05/2019 to 24/05/2019 Leave of Absence Unpaid then rescinded |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84729.htmld | Fail | 2019-06-19 |  | Graham Deneys (63002303) Rescinded the Unpaid Leave from 13/06/2019 to 03/11/2019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153447.htmld | Defect 4252 raised
TS_SSA_056 |  | LOA - Return from LOA | Return from Leave of absence | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | NP | ZA - Crimson Room Communication (Pty) Ltd | Pass | South Africa Richard Lewis (63002064) - 20/05/2019 - 24/05/2019 - Unpaid Leave corrected to return on 23/05/2019 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84729.htmld | File Sent | 2019-06-19 | SSA-20190619-150502-ATO.csv.pgp | Absence Return for Patricia Ntow (63002414) last day of absence on 18-Jun-2019, first day back at work on 19-Jun-2019
TS_SSA_058 |  | Maintain Payment Elections | Change payment type Note: Check with Country what mode of payment is used - N/A if only EFT/RTGS i.e. direct transfers are used. | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - John Brown South Africa (Pty) Ltd | Pass | Ricardo Bobbert 63002052, Account no. 1212121212 Univeral 045003. Savings Account |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152924.htmld | File Sent |  |  | Same data as test 057
TS_SSA_059 |  | Notifications | When an integration encounters Warning/Error/Failure. | A Notification is sent to the relevent roles | JA |  | Pass | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84776.htmld |  |  |  | N/A
TS_SSA_062 |  | OTP - Correction | Change amount for an OTP Request One Time Payment for employee | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | KE - Dentsu Aegis Network Kenya | Pass | Dora Awino 5014 Changed Referral from 50000 to 30000 |  | SSA-20190530-125948-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152930.htmld | File Sent | 12th June 2019 | SSA-20190612-203147-PAY.csv.pgp | Donald Mokgale (63002343) OTP increased by 3000 Sage ID : MOK001 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153348.htmld
TS_SSA_063 |  | OTP - Rescind | Rescind an OTP Request One Time Payment for employee | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Carat | Pass | Bithia Awuku-Asante 19023 - Rescinded Severance Pay. Added Spot 1000, and Overtime 2000 |  | SSA-20190530-130347-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152933.htmld | File Sent | 12th June 2019 | SSA-20190612-203504-PAY.csv.pgp | TestWill Test (63029237) Rescinded "South Africa - Spot Bonus" 20000 for 03/06/2019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153351.htmld
TS_SSA_070 |  | Request Compensation Change | Comp Change - Change Recurring Allowance to Employee - All Eligible Allowances for the Country | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Dentsu Aegis Network Zambia | Pass | Sikota Bones - 63006951 240003, Car Allownce 102, Education 103, General 104, Housing 105, Meal 106, Night 107, settling 108, Transport 109, Utility 110. | 4228 |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153045.htmld | File Sent | 12th June 2019 | SSA-20190612-203504-PAY.csv.pgp | All the allowances are increased by 6000. for employee 63029237 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153351.htmld
TS_SSA_071 |  | Request Compensation Change | Comp Change - Remove Recurring Allowance from Employee | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Vizeum | Pass | Fuseini Seidu Sahanoon Removed phone allowance |  | SSA-20190530-130916-PAY.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$152962.htmld | File Sent | 12th June 2019 | SSA-20190612-204538-PAY.csv.pgp | Removed two allowances effective 24th June and deleted 3 allowance from employee's record. 63002058 - Sage ID: 018_001 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153365.htmld
TS_SSA_073 |  | Request Compensation Change - Correction | Multiple Compensation correction for same date | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification. IT should pick up the last made change. | JA | ZA - John Brown South Africa (Pty) Ltd | Pass | Estelle Dietrich 63002059. Corrected Salary to 32000, removed cellphone allowance, changed end date of Travel allwance to 31/05/19 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$152989.htmld | File Sent | 12th June 2019 | SSA-20190612-204732-ETO.csv.pgp | 63002072 - SAGE ID - 056 salary changed to 718,659.84 ZAR |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153368.htmld
TS_SSA_074 |  | Request Compensation Change - Correction | Correct Comp Change effective date in current pay period - Change date - no other changes | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - Clickthinking Online (Pty) Ltd | Pass | Marco Martin 190. changed salary to 14000 230519, then changd date to 290519 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153036.htmld | File Sent | 2019-06-19 | SSA-20190619-150003-ATO.csv.pgp | changed the effective date to 06/05/2019 Estelle Dietrich (63002059) |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153458.htmld
TS_SSA_075 |  | Request Compensation Change - Correction | Correct Comp Change in current pay period - Change Pay - no other changes | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | ZA - MEC Carat (Pty) Ltd | Pass | Anna Van Wyk 2382 - corrected to 40002 |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153042.htmld | File Sent | 12th June 2019 | SSA-20190612-204732-ETO.csv.pgp | 63002072 - SAGE ID - 056 salary changed to 718,659.84 ZAR
TS_SSA_076 |  | Termination | Non - Starters (This employees should show as terminated) Note: Nigeria - performs a Termination, similarly check for other countries | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | Nigeria Pay Group | Pass | Testben Test- hire date - 08042019; Termination reason - non starter; termination date -08042019. | 4231 |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153422.htmld | Pass | 2019-06-19 | [7 empty] | The integration is designed not to send correction or Rescind as discussed prior. The rescind on hire or a non starter needs to be handled manually
TS_SSA_077 |  | Termination | Non - Starters (Check the expected behaviour on Technical Specification Document.) | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF |  | Pass |  |  |  |  | Pass | 2019-06-13 | File did not get generated | 63029240 - |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153395.htmld | The integration is designed not to send correction or Rescind as discussed prior. The rescind on hire or a non starter needs to be handled manually
TS_SSA_084 |  | Termination - Correction | Correct Termination Date | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF | ZA - John Brown South Africa (Pty) Ltd | Pass | joanne Hope 63002093/Termination date - 22/05/2019 corrected to 24/05/2019. |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$16107/697$84606.htmld | Pass | 2019-06-19 |  | Mogamat Daniels (63002171) Termination Date 06/05/2019 changed to 28/06/2019 |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153461.htmld | The integration is designed not to send correction or Rescind as discussed prior.
TS_SSA_085 |  | Termination - Rescind | Non - Leavers (Termination dates should get reset to 0 for this employees) | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | LF |  | Pass | Carol Thomas (63002330) - termination date - 30/05/2019 |  |  | No file produced | Pass | 2019-06-13 | File did not get generated | 63024792 - |  |  |  |  | https://wd3-impl.workday.com/dentsuaegis1/d/inst/1$427/2085$153392.htmld | The integration is designed not to send correction or Rescind as discussed prior. The rescind on hire or a non starter needs to be handled manually
TS_SSA_087 |  | Time Off - Correction | Correct Time Off | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Aegis Media Tanzania | Pass | Tanzania Henry Mbwille 16010 - Changed Sick Leave from 1 day to .5 days |  | SSA-20190529-101714-ATO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153250.htmld | File Sent | 2019-06-19 | SSA-20190619-150502-ATO.csv.pgp | Chesang Koech (63007923) 9th May 2019 made half a day
TS_SSA_088 |  | Time Off - Correction | Delete Time Off for current pay period. Using the "-" button on the row. | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | Aegis Media Nigeria | Pass | Chike Oputa 230112 - deleted study leave |  | SSA-20190529-102513-ATO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153253.htmld | File Sent | 2019-06-19 | SSA-20190619-150502-ATO.csv.pgp | Chesang Koech (63007923) 10th May 2019
TS_SSA_089 |  | Time Off - Correction | Delete Time Off for current pay period. Set the duration to "0" hours/Days for the day. | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Carat | Pass | Francis Sampson 18028 - Deleted exam leave |  | SSA-20190529-103204-ATO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153256.htmld | File Sent | 2019-06-19 | SSA-20190619-150502-ATO.csv.pgp | Chesang Koech (63007923) 6th May 2019
TS_SSA_090 |  | Time Off - Correction | Delete Time Off for previous pay period | Check the data inserted appears accurately on the Integration output file/Report as per the design Specification | JA | GH - Ghana Carat | Pass | Francis Sampson 18028 Deleted unpaid time off from 08/04 |  | SSA-20190529-104140-ATO.csv.pgp | https://wd3-impl.workday.com/dentsuaegis1/d/inst/15$30106/2085$153259.htmld | File Sent | 2019-06-19 | SSA-20190619-150502-ATO.csv.pgp | Chesang Koech (63007923)

## Test File Names
File Name | Comment | PAY File Name | ATO File Name | BEN File Name
SSA-20190605-084408-ETO.csv.pgp |  | SSA-20190605-093713-PAY.csv.pgp | SSA-20190607-124415-ATO.csv.pgp | SSA-20190605-093713-BEN.csv.pgp
SSA-20190605-093713-ETO.csv.pgp |  | SSA-20190605-102030-PAY.csv.pgp | SSA-20190613-160022-ATO.csv.pgp | SSA-20190606-124345-BEN.csv.pgp
SSA-20190605-094434-ETO.csv.pgp |  | SSA-20190605-104230-PAY.csv.pgp | SSA-20190619-150003-ATO.csv.pgp | SSA-20190606-130657-BEN.csv.pgp
SSA-20190605-094953-ETO.csv.pgp |  | SSA-20190606-125247-PAY.csv.pgp | SSA-20190619-150502-ATO.csv.pgp | SSA-20190613-124455-BEN.csv.pgp
SSA-20190605-102030-ETO.csv.pgp |  | SSA-20190606-130106-PAY.csv.pgp
SSA-20190605-102640-ETO.csv.pgp |  | SSA-20190606-130657-PAY.csv.pgp | Additional Files
SSA-20190605-103446-ETO.csv.pgp |  | SSA-20190606-135013-PAY.csv.pgp | SSA-20190607-130146-ATO
SSA-20190605-104230-ETO.csv.pgp |  | SSA-20190606-141623-PAY.csv.pgp | SSA-20190613-124455-ATO
SSA-20190606-124813-ETO.csv.pgp | File initially failed due to special characters | SSA-20190612-203147-PAY.csv.pgp | SSA-20190613-205608-ATO
SSA-20190606-125247-ETO.csv.pgp |  | SSA-20190612-203504-PAY.csv.pgp | SSA-20190613-210519-ATO
SSA-20190606-130106-ETO.csv.pgp |  | SSA-20190612-204538-PAY.csv.pgp | SSA-20190617-102232-ATO
SSA-20190606-130657-ETO.csv.pgp |  | SSA-20190613-124455-PAY.csv.pgp | SSA-20190619-094500-ATO
SSA-20190606-135013-ETO.csv.pgp |  |  | SSA-20190619-145948-ATO
SSA-20190607-130146-ETO.csv.pgp |  | Additional Files | SSA-20190619-154218-ATO
SSA-20190612-204732-ETO.csv.pgp |  | SSA-20190606-140933-PAY | SSA-20190620-113516-ATO
SSA-20190613-124455-ETO.csv.pgp |  | SSA-20190617-102232-PAY | SSA-20190620-120105-ATO
SSA-20190613-160022-ETO.csv.pgp |  | SSA-20190619-094500-PAY
SSA-20190619-145948-ETO.csv.pgp
SSA-20190619-163230-ETO.csv.pgp
Additional Files
SSA-20190605-092613-ETO
SSA-20190605-195029-ETO
SSA-20190611-092027-ETO
SSA-20190612-080004-ETO
SSA-20190619-094500-ETO
SSA-20190620-113516-ETO
SSA-20190620-120105-ETO

## Sage Processing Checks
File Origin | Queue Comments | Manual Actions | System Processing Comments | Warning Comment | Error Comment
0605_084408 | No errors |  | Processed Successfully
0605_092613 | No errors |  | Processed Successfully with some data warnings due to test data
0605_093713 | No errors |  | Processed Successfully with tax number warning
0605_094434 | No errors |  | Processed Successfully with warning due to insufficient field permissions on tax start date | Tax Start Date cannot be updated. Would need to be a new record
0605_094953 | Hold: Manual Transfer Required | Manual Transfer completed successfully | Processed Successfully
0605_102030 | No errors |  | Processed Successfully
0605_102640 | No errors |  | Processed Successfully with unrelated warnings
0605_103446 | No errors |  | Processed Successfully with warning to inform that account number won't be modified, but a new account will be created for auditing purposes
0605_104230 | Errors corrected |  | Processed With Success and Errors | No warnings for success records | Error Empls: 16023: Bank details required (This is due to a system issue where the employee was linked to ACB instead of Cash)
0606_125247 | No errors |  | Processed Successfully
0606_130106 | No errors |  | Processed Successfully
0606_130657 | No errors |  | Processed Successfully
0606_135013 | No errors |  | Processed Successfully
0606_124813 | Error loading CSV due to special characters
Empls with full address | Check file: 5062019_195029
Check employee: 63002256

## Absence Data
Country | WD Employee ID | Legacy Payroll ID | Employee Name | LOA Type | Time Off | Start Date | End Date
ZAF | 63002146 | 211 | Marina De Bruin (63002146) | South Africa-Maternity Leave |  | 2019-06-01 | 2020-02-29
ZAF | 63002243 | 2575 | Okkie Mathevula (63002243) |  | South Africa-Paternity Leave-Time Off | 2019-07-08 | 2019-07-16
ZAF | 63025485 |  | Fiona November (63025485) | South Africa-Sabbatical Leave |  | 2019-05-13 | 2019-08-31
ZAF | 63002303 | 266 | Graham Deneys (63002303) | South Africa-Unpaid Leave |  | 2019-06-13 | 2019-11-03
ZAF | 63002107 | 151 | Jill Harris (63002107) | South Africa-Unpaid Leave |  | 2019-06-24 | 2019-11-03
ZAF | 63002151 | 216 | Kyle Van Rooi (63002151) |  | South Africa-Sick Leave-Time Off | 2019-05-20 | 2019-06-23
GHA | 63002400 | 19025 | Kwame Appaw (63002400) | Ghana > Ghana-Leave of Absence (Paid) |  | 2019-05-01 | 2019-05-26
GHA | 63002395 | 18027 | John Teye (63002395) | Ghana > Ghana-Leave of Absence (Unpaid) |  | 2019-06-17 | 2019-06-30
GHA | 63002399 | 18035 | Kofi Owusu (63002399) | Ghana > Ghana-Long-Term Sick |  | 2019-04-29 | 2019-06-25
GHA | 63002414 | 19014 | Patricia Ntow (63002414) | Ghana > Ghana-Maternity Leave |  | 2019-04-29 | 2019-11-01
GHA | 63002395 | 18027 | John Teye (63002395) | Ghana > Ghana-Paternity Leave |  | 2019-06-03 | 2019-06-09
KEN | 63007927 |  | Fidel Halwenge (63007927) | Kenya > Kenya-Leave of Absence (Paid) |  | 2019-05-27 | 2019-06-09
KEN | 63007927 |  | Fidel Halwenge (63007927) | Kenya > Kenya-Leave of Absence (Unpaid) |  | 2019-06-14 | 2019-06-23
KEN | 63007889 |  | Isaiah Iraya (63007889) | Kenya > Kenya-Long-Term Sick |  | 2019-04-29 | 2019-09-01
KEN | 63007905 |  | Flavia Kassamani (63007905) | Kenya > Kenya-Maternity Leave |  | 2019-05-27 | 2020-02-02
KEN | 63007927 |  | Fidel Halwenge (63007927) | Kenya > Kenya-Paternity Leave |  | 2019-06-24 | 2019-06-28
NGA | 63002484 | 230091 | Lynda Iroegbu (63002484) | Nigeria > Nigeria-Leave of Absence (Paid) |  | 2019-06-03 | 2019-06-16
NGA | 63020102 | 230124 | Adewole Adeosun (63020102) | Nigeria > Nigeria-Leave of Absence (Unpaid) |  | 2019-06-17 | 2019-06-23
NGA | 63020102 | 230124 | Adewole Adeosun (63020102) | Nigeria > Nigeria-Long-Term Sick |  | 2019-06-24 | 2019-06-29
NGA | 63002484 | 230091 | Lynda Iroegbu (63002484) | Nigeria > Nigeria-Maternity Leave |  | 2019-06-17 | 2019-11-03
NGA | 63020102 | 230124 | Adewole Adeosun (63020102) | Nigeria > Nigeria-Paternity Leave |  | 2019-05-27 | 2019-06-02
Tanzania > Tanzania-Leave of Absence (Paid)
TZA | 63007741 | 16020 | Nawaz James (63007741) | Tanzania > Tanzania-Leave of Absence (Unpaid) |  | 2019-05-27 | 2019-06-02
TZA | 63007741 | 16020 | Nawaz James (63007741) | Tanzania > Tanzania-Long-Term Sick |  | 2019-06-17 | 2019-06-23
Tanzania > Tanzania-Maternity Leave
TZA | 63007741 | 16020 | Nawaz James (63007741) | Tanzania > Tanzania-Paternity Leave |  | 2019-06-24 | 2019-06-30
Zambia > Zambia-Leave of Absence (Paid)
Zambia > Zambia-Long-Term Sick
Zambia > Zambia-Leave of Absence (Unpaid)
Zambia > Zambia-Maternity Leave
Zambia > Zambia-Paternity Leave
GHA | 63022108 |  | Paa Woode (63022108) |  | Ghana-Annual Leave | 2019-06-03 | 2019-06-04
GHA | 63022108 |  | Paa Woode (63022108) |  | Ghana-Unpaid Leave | 2019-06-12 | 2019-06-14
GHA | 63022108 |  | Paa Woode (63022108) |  | Ghana-Sick Leave | 2019-06-17 | 2019-06-20
GHA | 63022108 |  | Paa Woode (63022108) |  | Ghana-Study/Exam Leave | 2019-06-25 | 2019-06-26
KEN | 63007923 |  | Chesang Koech (63007923) |  | Kenya-Annual Leave | 2019-05-06 | 2019-05-10
KEN | 63007923 |  | Chesang Koech (63007923) |  | Kenya-Unpaid Leave | 2019-06-10 | 2019-06-12
KEN | 63007923 |  | Chesang Koech (63007923) |  | Kenya-Sick Leave | 2019-07-01 | 2019-07-04
KEN | 63007923 |  | Chesang Koech (63007923) |  | Kenya-Study/Exam Leave | 2019-06-17 | 2019-06-18
NGA | 63002489 | 230075 | Alice Adeworan (63002489) |  | Nigeria-Annual Leave | 2019-05-20 | 2019-05-20
NGA | 63002489 | 230075 | Alice Adeworan (63002489) |  | Nigeria-Unpaid Leave | 2019-06-03 | 2019-06-05
NGA | 63002489 | 230075 | Alice Adeworan (63002489) |  | Nigeria-Sick Leave | 2019-06-24 | 2019-06-25
NGA | 63002489 | 230075 | Alice Adeworan (63002489) |  | Nigeria-Study/Exam Leave | 2019-06-10 | 2019-06-14
ZAF | 63002279 | 2632 | Gregory Wendzicha (63002279) |  | South Africa-Family Responsibility | 2019-06-24 | 2019-06-26
ZAF | 63002279 | 2632 | Gregory Wendzicha (63002279) |  | South Africa-Study/Exam Leave | 2019-06-10 | 2019-06-14
ZAF | 63002279 | 2632 | Gregory Wendzicha (63002279) |  | South Africa-Annual Leave | 2019-05-27 | 2019-06-07
ZAF | 63002279 | 2632 | Gregory Wendzicha (63002279) |  | South Africa-Birthday Leave | DOESN'T APPEAR
ZAF | 63002279 | 2632 | Gregory Wendzicha (63002279) |  | South Africa-1% leave | DOESN'T APPEAR
TZA | 63002380 | 16017 | Evelyn Auguste (63002380) |  | Tanzania-Annual Leave | 2019-05-01 | 2019-05-22
TZA | 63002380 | 16017 | Evelyn Auguste (63002380) |  | Tanzania-Unpaid Leave | 2019-05-23 | 2019-05-31
TZA | 63002380 | 16017 | Evelyn Auguste (63002380) |  | Tanzania-Sick Leave | 2019-06-10 | 2019-06-13
TZA | 63002380 | 16017 | Evelyn Auguste (63002380) |  | Tanzania-Family Responsibility | 2019-06-24 | 2019-06-26
TZA | 63002380 | 16017 | Evelyn Auguste (63002380) |  | Tanzania-Study/Exam Leave | 2019-07-01 | 2019-07-05
ZMB | 63006950 | 240002 | Jessica Kanyuka (63006950) |  | Zambia-Annual Leave | 2019-05-13 | 2019-05-17
ZMB | 63006950 | 240002 | Jessica Kanyuka (63006950) |  | Zambia-Unpaid Leave | 2019-05-20 | 2019-05-23
ZMB | 63006950 | 240002 | Jessica Kanyuka (63006950) |  | Zambia-Sick Leave | 2019-06-03 | 2019-06-04
ZMB | 63006950 | 240002 | Jessica Kanyuka (63006950) |  | Zambia-Study/Exam Leave | 2019-06-05 | 2019-06-07
ZMB | 63006950 | 240002 | Jessica Kanyuka (63006950) |  | Zambia-Family Responsibility | 2019-06-12 | 2019-06-14

## Unit Scenarios (hidden)
Type | BP | Test Conditions | Expected
Employee is not picked up in the file till the hire date
Error Handling with integration
Checking Diagnostic Audit file for failed users
SFTP file delivery test
Format for the file being delivered is as per the specification
Separators used on the deliverable file is as per the specification
Intgration to output Full File
Intgration to output Update only File
Headers are named as per the specification
Blank Rows to appear if specified on the design Document
last line on the output file should not be Blank until it is specified on the Design Document
Correct Error Description / Information is displayed for any Failed Integrations
New Line Character on a free text field should not break during Document transformation
Old data is also captured and shown on the file it is in the requirements